## 3x3 Stage Matrix
Layer | Stage A — Vertical Slice MVP 9-12 months | Stage B — Expansion +12-18 months | Stage C — Industry +18-30 months
DATA (What is in the DB?) | Scope: Alpha Ventus (12 turbines) + Emden port POPULATED (real data): - wind_farms: Alpha Ventus only (4C + BNetzA) - turbines: 12x REpower 5M / AREVA M5000 - turbine_types: 2 types (REpower 5M, AREVA M5000) - materials + bom_items: BOM-Light (~20 rows, Vestas/IRENA proxy) - ports: 1 (Emden), basic attributes - vessels: 3-5 reference vessels (manual) - metocean_monthly: ERA5 for Alpha Ventus location - natura2000_areas: Overlap check for Alpha Ventus - permits: BSH approval Alpha Ventus - process_chain_phases: 12 EoL phases (seed data) - disassembly_steps: DAG for REpower 5M (literature + Marc) SCHEMA-READY (empty, structure exists): - transport_legs, port_operations, recycling_outcomes - scrap_prices, mass_scaling_models, material_splits - dpp_passports, dpp_fields - circularity_kpis, eol_scenarios - lca_results, impact_categories - simulation_runs ETL: 3-4 actual pipelines 1) 4C CSV import (wind farms + turbines) 2) ERA5 NetCDF download + monthly aggregation 3) BfN/EEA GeoJSON (Natura2000, one-time) 4) Manual CSV imports (BOM, ports, vessels) Infrastructure: PostGIS, RLS, Provenance, Partitioning | Scope: 5-10 German North Sea parks + 2-3 ports + All DE offshore parks from 4C (BARD, Meerwind, ...) + 2-3 ports (Emden, Cuxhaven, Bremerhaven) + ERA5 daily resolution (not just monthly) + ecoinvent background data (SimaPro license) + CMEMS ocean currents + BOM for 3-5 turbine types + Recycler basic data (Stena, TSR, ...) + Searoutes distance matrices + Clarkson vessel specs (if budget allows) + WindEurope pipeline data (build-out wave) + 2-3 additional ETL pipelines | Scope: Full North Sea + Baltic + Full OEM BOMs (industry partner required) + SCADA / operational data + AIS vessel tracking (real-time) + Actual decom costs (industry partner) + Multi-tenant data separation + NL, DK, UK parks
ANALYSIS (What can be computed?) | SQL views + heuristics (Alpha Ventus only): - Decom timeline (when does Alpha Ventus expire?) - Material flow estimate (BOM x 12 turbines) - Weather window statistics (operable days/quarter) - Harbour distance (PostGIS ST_Distance to Emden) - Natura2000 overlap check (ST_Intersects) - Critical raw materials inventory - EoL process chain visualization LCA: - 1x probe LCA for 1 turbine (EoL phase) - LCA proxies (IRENA/Vestas aggregates) Simulation: - 1x AnyLogic run (Alpha Ventus, Emden, 1 strategy) All calculations reproducible via data_quality_log | + Scenario comparison (Reverse Install vs Heavy Lift) + Multi-port optimization (AnyLogic) + Build-out / decom conflict analysis + LCA with ecoinvent (no more proxies) + Cost model (charter + port fees) + Sensitivity analysis (scrap prices, weather) + Recycler matching (material -> recycler) + Vessel type recommendation per turbine type + Policy advisory reports | + Real-time campaign planning + Predictive maintenance -> condition-based decom + Multi-stakeholder optimization (cost/CO2/time) + Monte Carlo simulation (uncertainties) + Digital twin (live sync) + Automated tender generation
PRODUCT (What does the user see?) | Core Product A: Decom Capacity Screener (MVP) - Interactive map (Alpha Ventus + Emden) - Decom timeline (single park view) - Material flow estimate (bar charts) - Weather window calendar - Harbour info card (Emden) Research Product B: DPP Prototype - 1x AASX export (1 Alpha Ventus turbine) - DPP completeness dashboard - JSON-LD serialization Platform: - REST API v1 (CRUD + data contracts) - Supabase admin dashboard - CSV/JSON import function | + Multi-park screener (filters, comparison) + Port ranking table (Top-5 per park) + Scenario dashboard (what-if) + Cost comparison decom strategies + DPP for 3-5 turbine types + Policy brief generator + Public API (read-only) + Build-out wave overlay on map | + SaaS platform (multi-tenant) + Real-time dashboard + Tender assistant + Stakeholder portal (OEM, port, recycler) + Automatic DPP generation + Mobile app (offshore inspections) + Secondary raw materials marketplace

## Schema v1.1 — Honest Count
# | Table | Domain | Stage A Status | Data in Stage A | ETL Source | ETL Method
1 | wind_farms | Asset Registry | POPULATED | Alpha Ventus (1 park) | 4C CSV + BNetzA | CSV import script
2 | turbines | Asset Registry | POPULATED | 12 turbines (Alpha Ventus) | 4C CSV | CSV import script
3 | turbine_types | Asset Registry | POPULATED | 2 types (REpower 5M, AREVA M5000) | 4C + OEM specs | Manual entry
4 | materials | BOM | POPULATED | ~9 material classes | Vestas LCA, IRENA, TU Delft | Manual CSV
5 | bom_items | BOM | POPULATED | ~20 rows (proxy BOM-Light) | Vestas LCA Ch.4 | Manual CSV
6 | impact_categories | LCA | SEED | ~18 CML-IA categories | JRC / CML-IA standard | Seed script
7 | lca_results | LCA | SCHEMA ONLY | Empty until Thomas runs probe-LCA | SimaPro/openLCA | CSV from Thomas
8 | circularity_kpis | Circularity | SCHEMA ONLY | Calculated after LCA results exist | Calculation | SQL/Python
9 | eol_treatment_rates | Circularity | POPULATED | ~9 rows (per material) | IRENA, TU Delft | Manual CSV
10 | eol_scenarios | Circularity | POPULATED | ~5 scenarios from TU Delft thesis | TU Delft | Manual CSV
11 | scrap_prices | Market | POPULATED | ~9 materials x 2 dates (2020, 2026) | LME, industry reports | Manual CSV
12 | mass_scaling_models | Scaling | POPULATED | ~8 equations from TU Delft | TU Delft thesis | Manual CSV
13 | material_splits | Scaling | POPULATED | ~15 rows (component x material) | TU Delft thesis | Manual CSV
14 | metocean_monthly | Metocean | POPULATED | Alpha Ventus location, 2020-2025 | ERA5 (Copernicus) | NetCDF pipeline
15 | ports | Logistics | POPULATED | 1 port (Emden), basic attributes | Public + domain knowledge | Manual entry
16 | vessels | Logistics | POPULATED | 3-5 reference vessels | Domain knowledge (Marc) | Manual entry
17 | natura2000_areas | Regulatory | POPULATED | Areas overlapping Alpha Ventus | BfN/EEA | GeoJSON import
18 | permits | Regulatory | POPULATED | BSH approvals Alpha Ventus | BSH public | Manual entry
19 | dpp_passports | DPP | SCHEMA ONLY | Created after Phase 2 integration | Generated | API/Script
20 | dpp_fields | DPP | SCHEMA ONLY | Created after Phase 2 integration | All modules | API/Script
21 | lifecycle_events | Lifecycle | POPULATED | Installation + key events Alpha Ventus | 4C, BSH | Manual CSV
22 | process_chain_phases | Process Chain | SEED | 12 EoL phases (reference data) | ASTRA-defined | Seed script
23 | disassembly_steps | Process Chain | POPULATED | DAG for REpower 5M (~15-20 steps) | Literature + Marc | Manual entry
24 | transport_legs | Process Chain | SCHEMA ONLY | Filled by AnyLogic output (Phase 2-3) | AnyLogic | API/CSV
25 | port_operations | Process Chain | SCHEMA ONLY | Filled by AnyLogic output (Phase 2-3) | AnyLogic | API/CSV
26 | recycling_outcomes | Process Chain | SCHEMA ONLY | Filled after simulation + LCA (Phase 3) | Calculation | SQL/Python
27 | data_sources | Provenance | SEED | ~7 source entries | ASTRA-defined | Seed script
28 | data_quality_log | Provenance | AUTO | Populated automatically by ETL | Automatic | Trigger
29 | etl_runs | Provenance | AUTO | Populated automatically by ETL | Automatic | Trigger
30 | simulation_runs | Simulation | SCHEMA ONLY | After Marc runs first AnyLogic (Phase 2) | AnyLogic | API
Summary:
| POPULATED (real data in Stage A): | 18 tables
| SEED (reference/config data): | 3 tables
| AUTO (filled by system): | 2 tables
| SCHEMA ONLY (empty until Phase 2-3): | 7 tables
| Total: | 30 core tables + 6 partitions + 5 views = 41 objects
| Actual ETL pipelines in Stage A: | 3-4 (not 7+)
| 1) 4C CSV import | wind_farms + turbines + turbine_types
| 2) ERA5 NetCDF pipeline | metocean_monthly (monthly aggregates)
| 3) BfN/EEA GeoJSON import | natura2000_areas (one-time)
| 4) Manual CSV imports | BOM, ports, vessels, permits, scrap_prices, scaling models

## Process Chain Mapping
# | Real Process Step | Location | DB Table(s) | Stage A Data | AnyLogic Role
1 | Manufacturing (OEM) | Factory | turbine_types, bom_items, materials | BOM-Light proxy (Vestas/IRENA) | -
2 | Transport & Installation | Sea + Offshore | lifecycle_events | 4C/BNetzA dates | -
3 | Operation (20-25 yrs) | Offshore | lifecycle_events | 4C/BSH historical | -
4 | Permitting & Preparation | Onshore | permits, process_chain_phases[PREP] | BSH approvals | Parameter
5 | Offshore Disconnection | Offshore | disassembly_steps[DISCONNECT] | Literature + Marc | INPUT
6 | Offshore Disassembly | Offshore | disassembly_steps[DISASSEMBLY] | Literature + Marc | INPUT
7 | Foundation Removal | Offshore | disassembly_steps[FOUNDATION] | Literature + Marc | INPUT
8 | Cable Removal | Offshore | disassembly_steps[CABLE] | BSH requirements | INPUT
9 | Sea Transport | Transit (sea) | transport_legs (sea) | PostGIS distance calc | OUTPUT
10 | Port Receiving | Port (Emden) | port_operations[receiving] | Emden basic data | OUTPUT
11 | Onshore Dismantling | Port (Emden) | port_operations[dismantling] | Domain knowledge | OUTPUT
12 | Material Separation | Port (Emden) | port_operations[sorting] | Derived from BOM | OUTPUT
13 | Transport to Recycler | Road/Rail | transport_legs (road/rail) | Hinterland proxy | OUTPUT
14 | Recycling | Recycler | recycling_outcomes | IRENA proxy rates | OUTPUT
15 | Disposal | Landfill/Incin. | recycling_outcomes | eol_treatment_rates | OUTPUT

## Complexity Profile
Dimension | ASTRA (Schema v1.1) | Stage A Reality | Typical Research Project | Factor vs Typical
Tables in schema | 30 core + 6 partitions | 30 (but 7 empty until Phase 2-3) | 8-12 | ~3x
Tables with data (Stage A) | - | 18 populated + 3 seed + 2 auto = 23 | 8-12 | ~2x
Views | 5 | 5 | 1-2 | ~3x
Data sources | 10+ heterogeneous | 4 actual sources (4C, ERA5, BfN, manual) | 2-3 | ~1.5x
ETL pipelines | Schema supports 7+ | 3-4 actual (CSV, NetCDF, GeoJSON, manual) | 1-2 | ~2x
Formats | CSV, NetCDF, GeoJSON, JSON, PDF | CSV + NetCDF + GeoJSON | CSV only | ~2x
Relations | Complex, cross-domain | Complex, cross-domain | Simple, 1:n | ~4x
PostGIS required | Yes (3 geo tables, spatial queries) | Yes (wind_farms, ports, natura2000) | No | Unique
Timeseries partitioning | Yes (metocean_monthly) | Yes (6 yearly partitions) | No | Unique
DAG modeling | Yes (disassembly_steps) | Yes (predecessor_steps[]) | No | Unique
RLS (Row Level Security) | Yes, on all 30 tables | Yes, but single-role in Stage A | No | Unique
Audit / Provenance | Yes (3 tables) | Yes | No | Unique
EoL process chain | 12 phases, 5 tables | 12 phases defined, 2-3 populated | - | Unique
DPP/AAS integration | Yes (2 tables + AASX export) | Schema ready, 1 export in Phase 2-3 | - | Unique
Parks with data | - | 1 (Alpha Ventus) | 1-2 | 1x
Ports with data | - | 1 (Emden) | 0-1 | 1x

## Kickoff Alignment
Kickoff Decision (Feb/Mar 2026) | Source | Schema v1.1 Implementation | Aligned?
Vertical Slice first, then expand | Kickoff Decision #2 | Stage A = Alpha Ventus only. Schema supports expansion but no data for other parks. | YES
Alpha Ventus as pilot park | Vertical Slice (Sec 7) | wind_farms + turbines populated for Alpha Ventus only | YES
3-5 representative vessels | Vertical Slice (Sec 7) | vessels table with 3-5 manual entries | YES
Port: Emden | Vertical Slice (Sec 7) | ports table with 1 entry (Emden) | YES
1 recycler | Vertical Slice (Sec 7) | recycling_outcomes schema ready; recycler as text field (not own table) | YES
Colombo 4-step framework | Decision (Sec 8) | Schema follows: Products -> Data needs -> Data prep -> Sources | YES
Supabase backend | Heiko Stack (Sec 15.2) | Full Supabase schema with RLS, PostGIS, Auth | YES
Next.js frontend | Heiko Stack (Sec 15.2) | Not in DB schema (frontend layer) | N/A
AnyLogic bidirectional | Marc Architecture (Sec 15.1) | simulation_runs (JSONB params + results), disassembly_steps as input | YES
DPP-Light / AAS | Colombo + Shubham (Sec 17) | dpp_passports + dpp_fields; AAS submodel mapping | YES
BOM focus on steel + key materials | BOM (Sec 5.3) | bom_items with ~20 rows, ~9 material classes | YES
EMODnet + Copernicus as free base layers | Data (Sec 5.2) | ERA5 (Copernicus) implemented; EMODnet not yet needed | PARTIAL
4C Academic Insights license | Data (Sec 5.1) | Schema assumes 4C data import; license status: secured | YES
SimaPro license ~9400 EUR | Budget (Sec 6) | lca_results schema ready; openLCA as fallback | PARTIAL
Platform scope risk: multi-year task | Risk (Sec 10) | Staged approach (A/B/C) mitigates; schema is complete but data is focused | YES
Resource scarcity risk | Risk (Sec 10) | 3x3 matrix makes scope explicit; can descope to schema-only for late tables | YES